## SPASS
Request | Riders | Start (SCET) | Start (Epoch) | Duration | End | Primary | Secondary | Comments
Sequence S94, length = 69 days |  | 2016-109T18:43:00 |  | 068T21:01:00 | 2016-178T15:44:00
XD_235 Segment |  | 2016-109T18:43:00 |  | 015T00:46:00 | 2016-124T19:29:00
SP_235EA_S94IVP109_PRIME |  | 2016-109T18:43:00 |  | 000T00:06:00 | 2016-109T18:49:00 | XBAND to Earth | NEG_X to 270.0/68.0 | S94 IVP Gap
ENGR_235SC_RWABIAS109_PRIME |  | 2016-109T18:49:00 |  | 000T01:30:00 | 2016-109T20:19:00 | XBAND to Earth | NEG_X to 270.0/68.0
SP_235EA_DLTURN109_PRIME |  | 2016-109T20:19:00 |  | 000T00:21:00 | 2016-109T20:40:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-109T20:40:00 |  | 000T17:48:00 | 2016-110T14:28:00 | XBAND to Earth | NEG_X to 320.0/45.0
CDA_235DR_EXOGEN001_PRIME |  | 2016-109T20:40:00 |  | 000T07:18:00 | 2016-110T03:58:00 | XBAND to Earth | Rolling
SP_235EA_YGAP110_PRIME | M | 2016-110T03:58:00 |  | 000T01:30:00 | 2016-110T05:28:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34BWGNON110_PRIME | C, M | 2016-110T05:28:00 |  | 000T08:30:00 | 2016-110T13:58:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 320/45.SRU.
SP_235SA_WAYPTTURN110_PRIME | M | 2016-110T13:58:00 |  | 000T00:30:00 | 2016-110T14:28:00 | ISS_NAC to Saturn | POS_Z to 189.3/66.9
NEW WAYPOINT |  | 2016-110T14:28:00 |  | 000T13:15:00 | 2016-111T03:43:00 | ISS_NAC to Saturn | POS_Z to 189.3/66.9
ISS_235TI_M60R3CLD110_PRIME | C, I, M, V | 2016-110T14:28:00 | E235_M60R3CLD110+000T00:00:00 | 000T01:30:00 | 2016-110T15:58:00 | ISS_NAC to Titan | POS_Z to 189.3/66.9 | No Preference to secondary pointing
CIRS_235SA_COMPSIT001_PRIME | I, M, U, V | 2016-110T15:58:00 |  | 000T11:10:00 | 2016-111T03:08:00 | CIRS_FP3 to Saturn | POS_Z to 189.3/66.9
SP_235EA_DLTURN111_PRIME |  | 2016-111T03:08:00 |  | 000T00:35:00 | 2016-111T03:43:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-111T03:43:00 |  | 001T10:40:00 | 2016-112T14:23:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_YGAP111_PRIME |  | 2016-111T03:43:00 |  | 000T01:30:00 | 2016-111T05:13:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34B26NON111_PRIME | C, R | 2016-111T05:13:00 |  | 000T08:30:00 | 2016-111T13:43:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 320/45.SRU.
CDA_235DR_EXOGEN003_PRIME | M | 2016-111T14:43:00 |  | 000T09:00:00 | 2016-111T23:43:00 | XBAND to Earth | Rolling
SP_235EA_YGAP112_PRIME | M | 2016-112T03:43:00 |  | 000T01:30:00 | 2016-112T05:13:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34BWGNON112_PRIME | C, M, R | 2016-112T05:13:00 |  | 000T08:30:00 | 2016-112T13:43:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 320/45.SRU.
SP_235SA_WAYPTTURN112_PRIME | M | 2016-112T13:43:00 |  | 000T00:40:00 | 2016-112T14:23:00 | ISS_NAC to Saturn | POS_Z to 189.3/66.9
NEW WAYPOINT |  | 2016-112T14:23:00 |  | 000T19:10:00 | 2016-113T09:33:00 | ISS_NAC to Saturn | POS_Z to 189.3/66.9
ISS_235TI_M60R3CLD112_PRIME | C, M, V | 2016-112T14:23:00 | E235_M60R3CLD112+000T00:00:00 | 000T01:30:00 | 2016-112T15:53:00 | ISS_NAC to Titan | POS_Z to 189.3/66.9 | No Preference to secondary pointing
ISS_235OT_SATELLORB004_PRIME | I, M, V | 2016-112T15:53:00 |  | 000T01:00:00 | 2016-112T16:53:00 | ISS_NAC to Satellites | POS_Z to 189.3/66.9 | Must point within 15 deg of Saturn Center
CIRS_235SA_MIRTMAP001_PRIME | I, M, V | 2016-112T16:53:00 |  | 000T16:00:00 | 2016-113T08:53:00 | CIRS_FP3 to Saturn | POS_Z to 189.3/66.9
SP_235EA_DLTURN113_PRIME |  | 2016-113T08:53:00 |  | 000T00:40:00 | 2016-113T09:33:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-113T09:33:00 |  | 001T11:20:00 | 2016-114T20:53:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_C34BWGOTP113_PRIME | C, E, N | 2016-113T11:13:00 |  | 000T09:00:00 | 2016-113T20:13:00 | XBAND to Earth | 4_Hr_Rolling | CDA.NEG_X to 320/45.OTP.SRU.
CDA_235DR_EXOGEN004_PRIME |  | 2016-113T21:13:00 |  | 000T09:00:00 | 2016-114T06:13:00 | XBAND to Earth | Rolling
CDA_235DR_EXOGEN005_PRIME |  | 2016-114T07:13:00 |  | 000T03:00:00 | 2016-114T10:13:00 | XBAND to Earth | Rolling
SP_235EA_C34BWGOTB114_PRIME | C, N | 2016-114T11:13:00 |  | 000T09:00:00 | 2016-114T20:13:00 | XBAND to Earth | 4_Hr_Rolling | CDA.same secondary as OTP pass.OTB.SRU.
SP_235SA_WAYPTTURN114_PRIME |  | 2016-114T20:13:00 |  | 000T00:40:00 | 2016-114T20:53:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
NEW WAYPOINT |  | 2016-114T20:53:00 |  | 000T13:07:00 | 2016-115T10:00:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
ISS_235TI_M60R3CLD114_PRIME | C, V | 2016-114T20:53:00 | E235_M60R3CLD114+000T00:00:00 | 000T01:30:00 | 2016-114T22:23:00 | ISS_NAC to Titan | NEG_X to 189.3/66.9 | No Preference to secondary pointing
ISS_235OT_SATELLORB006_PRIME | C, I, V | 2016-114T22:23:00 |  | 000T01:00:00 | 2016-114T23:23:00 | ISS_NAC to Satellites | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
CIRS_235RA_COMPLLRES001_PRIME | C, I, U, V | 2016-114T23:23:00 |  | 000T10:00:00 | 2016-115T09:23:00 | CIRS_FP1 to Rings | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
SP_235EA_DLTURN115_PRIME |  | 2016-115T09:23:00 |  | 000T00:37:00 | 2016-115T10:00:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-115T10:00:00 |  | 003T04:08:00 | 2016-118T14:08:00 | XBAND to Earth | NEG_X to 320.0/45.0
CIRS_235ST_ECSTARCAL012_PRIME | C | 2016-115T10:00:00 |  | 000T10:13:00 | 2016-115T20:13:00 | CIRS_FP3 to 161.265/-59.684 | PIC | Jettison Activity. Will be deleted if RBOT issues occur.
SP_235EA_YGAP115_PRIME |  | 2016-115T20:13:00 |  | 000T01:30:00 | 2016-115T21:43:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_M70METNON115_PRIME | C | 2016-115T21:43:00 |  | 000T06:00:00 | 2016-116T03:43:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235EA_M70METUNQ515_PRIME | C, U | 2016-116T03:43:00 |  | 000T02:00:00 | 2016-116T05:43:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
ISS_235SA_SATSTARE001_PRIME | C, V | 2016-116T05:43:00 |  | 001T21:30:00 | 2016-118T03:13:00 | ISS_WAC to Saturn | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
ENGR_235SC_RWABIAS118_PRIME |  | 2016-118T03:13:00 |  | 000T01:30:00 | 2016-118T04:43:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34HEFNON118_PRIME | C | 2016-118T04:43:00 |  | 000T08:45:00 | 2016-118T13:28:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235SA_WAYPTTURN118_PRIME |  | 2016-118T13:28:00 |  | 000T00:40:00 | 2016-118T14:08:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
NEW WAYPOINT |  | 2016-118T14:08:00 |  | 000T21:52:00 | 2016-119T12:00:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
ISS_235TI_M90R3CLD118_PRIME | C, V | 2016-118T14:08:00 | E235_M90R3CLD118+000T00:00:00 | 000T01:30:00 | 2016-118T15:38:00 | ISS_NAC to Titan | NEG_X to 88.251/9.968
ISS_235OT_SATELLORB008_PRIME | I, V | 2016-118T15:38:00 |  | 000T01:00:00 | 2016-118T16:38:00 | ISS_NAC to Satellites | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
ISS_235RI_ARCORBIT001_PRIME | C, I | 2016-118T16:38:00 |  | 000T19:00:00 | 2016-119T11:38:00 | ISS_NAC to Rings | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
SP_235EA_DLTURN119_PRIME |  | 2016-119T11:38:00 |  | 000T00:22:00 | 2016-119T12:00:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-119T12:00:00 |  | 002T01:40:00 | 2016-121T13:40:00 | XBAND to Earth | NEG_X to 320.0/45.0
ISS_235OT_TARPOL109_PRIME | V | 2016-119T12:00:00 |  | 000T13:14:00 | 2016-120T01:14:00 | UVIS_FUV to Rocks | NEG_Z to Earth | Jettison Activity. Will be deleted if RBOT issues occur.
MAG_235SU_CALROLL001_PRIME | U | 2016-120T01:14:00 |  | 000T08:00:00 | 2016-120T09:14:00 | NEG_X to Earth (0.0,0.0,-30.0 deg. offset) | Rolling
SP_235EA_YGAP120_PRIME |  | 2016-120T09:14:00 |  | 000T01:30:00 | 2016-120T10:44:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_C70METNON120_PRIME | C, R | 2016-120T10:44:00 |  | 000T09:00:00 | 2016-120T19:44:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235EA_YGAP121_PRIME |  | 2016-121T03:14:00 |  | 000T01:30:00 | 2016-121T04:44:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34HEFNON121_PRIME | C | 2016-121T04:44:00 |  | 000T08:30:00 | 2016-121T13:14:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235SA_WAYPTTURN121_PRIME |  | 2016-121T13:14:00 |  | 000T00:26:00 | 2016-121T13:40:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
NEW WAYPOINT |  | 2016-121T13:40:00 |  | 000T13:19:00 | 2016-122T02:59:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
ISS_235TI_M60R3CLD121_PRIME | C, I, V | 2016-121T13:40:00 | E235_M60R3CLD121+000T00:00:00 | 000T01:30:00 | 2016-121T15:10:00 | ISS_NAC to Titan | NEG_X to 189.3/66.9 | No Preference to secondary pointing
CIRS_235SA_FIRMAP001_PRIME | I, V | 2016-121T15:10:00 |  | 000T11:20:00 | 2016-122T02:30:00 | CIRS_FP1 to Saturn | NEG_X to NSP
SP_235EA_DLTURN122_PRIME |  | 2016-122T02:30:00 |  | 000T00:29:00 | 2016-122T02:59:00 | XBAND to Earth | NEG_X to 320.0/45.0
NEW WAYPOINT |  | 2016-122T02:59:00 |  | 000T10:20:00 | 2016-122T13:19:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_YGAP122_PRIME |  | 2016-122T02:59:00 |  | 000T01:30:00 | 2016-122T04:29:00 | XBAND to Earth | NEG_X to 320.0/45.0
SP_235EA_G34BWGNON122_PRIME | C | 2016-122T04:29:00 |  | 000T08:30:00 | 2016-122T12:59:00 | XBAND to Earth | NEG_X to 320.0/45.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235EA_DLTURN522_PRIME |  | 2016-122T12:59:00 |  | 000T00:20:00 | 2016-122T13:19:00 | XBAND to Earth | NEG_X to 356.0/-29.0
NEW WAYPOINT |  | 2016-122T13:19:00 |  | 001T00:16:00 | 2016-123T13:35:00 | XBAND to Earth | NEG_X to 356.0/-29.0
ISS_235RF_FMOVIE001_PRIME | C, V | 2016-122T13:19:00 |  | 000T13:40:00 | 2016-123T02:59:00 | ISS_NAC to Rings | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
ENGR_235SC_KPTYBIAS123_PRIME |  | 2016-123T02:59:00 |  | 000T01:30:00 | 2016-123T04:29:00 | NEG_Z to DELTA_H (0.0,0.0,-35.002 deg. offset) | NEG_X to Sun
SP_235EA_G34BWGNON123_PRIME | C | 2016-123T04:29:00 |  | 000T08:30:00 | 2016-123T12:59:00 | XBAND to Earth | NEG_X to 356.0/-29.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_235SA_WAYPTTURN123_PRIME |  | 2016-123T12:59:00 |  | 000T00:36:00 | 2016-123T13:35:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
NEW WAYPOINT |  | 2016-123T13:35:00 |  | 000T20:54:00 | 2016-124T10:29:00 | ISS_NAC to Saturn | NEG_X to 189.3/66.9
ISS_235TI_M60R3CLD123_PRIME | C, V | 2016-123T13:35:00 | E235_M60R3CLD123+000T00:00:00 | 000T01:30:00 | 2016-123T15:05:00 | ISS_NAC to Titan | NEG_X to 189.3/66.9 | No Preference to secondary pointing
ISS_235OT_SATELLORB012_PRIME | C, I, V | 2016-123T15:05:00 |  | 000T01:00:00 | 2016-123T16:05:00 | ISS_NAC to Satellites | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
UVIS_235SA_AURSLEW001_PRIME | C, V | 2016-123T16:05:00 |  | 000T08:55:00 | 2016-124T01:00:00 | UVIS_FUV to Saturn | NEG_X to 189.3/66.9 | Collaborative Rider(s): VIMS. must point within 15 deg. of Saturn center
CIRS_235RH_COMPGLBL001_PRIME | C, U, V | 2016-124T01:00:00 |  | 000T06:00:00 | 2016-124T07:00:00 | CIRS_FP1 to Rhea | NEG_X to 189.3/66.9 | Collaborative Rider(s): UVIS. No Preference to secondary pointing
ISS_235RI_PROPRETRG001_PRIME | C | 2016-124T07:00:00 |  | 000T02:54:00 | 2016-124T09:54:00 | ISS_NAC to Rings (-0.006,13.0,0.0 deg. offset) | NEG_X to 189.3/66.9 | Must point within 15 deg of Saturn Center
SP_235EA_DLTURN124_PRIME |  | 2016-124T09:54:00 |  | 000T00:35:00 | 2016-124T10:29:00 | XBAND to Earth | NEG_X to 356.0/-29.0
NEW WAYPOINT |  | 2016-124T10:29:00 |  | 000T09:40:00 | 2016-124T20:09:00 | XBAND to Earth | NEG_X to 356.0/-29.0
SP_235EA_C70METOTP124_PRIME | C, N | 2016-124T10:29:00 |  | 000T09:00:00 | 2016-124T19:29:00 | XBAND to Earth | NEG_X to 356.0/-29.0 | No Roll per AACS 2 of 3 Rule. Secondary chosen for CDA.
SATURN_235 Segment |  | 2016-124T19:29:00 |  | 001T23:45:00 | 2016-126T19:14:00
SP_235SA_WAYPTTURN124_PRIME |  | 2016-124T19:29:00 |  | 000T00:40:00 | 2016-124T20:09:00 | ISS_NAC to Saturn | NEG_X to NSP
NEW WAYPOINT |  | 2016-124T20:09:00 |  | 000T14:20:00 | 2016-125T10:29:00 | ISS_NAC to Saturn | NEG_X to NSP
VIMS_235SA_NHEMMAP001_PRIME | C, I | 2016-124T20:09:00 |  | 000T02:40:00 | 2016-124T22:49:00 | ISS_NAC to Saturn | NEG_X to NSP | Collaborative Rider(s): ISS
VIMS_235SA_SHEMMAP001_PRIME | C, I, M | 2016-124T22:49:00 |  | 000T11:00:00 | 2016-125T09:49:00 | ISS_NAC to Saturn | NEG_X to NSP | Collaborative Rider(s): ISS
SP_235EA_DLTURN125_PRIME |  | 2016-125T09:49:00 |  | 000T00:40:00 | 2016-125T10:29:00 | XBAND to Earth | NEG_X to 356.0/-29.0
NEW WAYPOINT |  | 2016-125T10:29:00 |  | 000T09:40:00 | 2016-125T20:09:00 | XBAND to Earth | NEG_X to 356.0/-29.0
SP_235EA_C34BWGOTB125_PRIME | C, E, N | 2016-125T10:29:00 |  | 000T09:00:00 | 2016-125T19:29:00 | XBAND to Earth | 4_Hr_Rolling | CAPS.same secondary as OTP pass.OTB.SRU.
Periapse R = 8.330 Rs, lat ... |  | 2016-125T16:34:07 |  | 000T00:00:01 | 2016-125T16:34:08
SP_235SA_WAYPTTURN126_PRIME |  | 2016-125T19:29:00 |  | 000T00:40:00 | 2016-125T20:09:00 | ISS_NAC to Saturn (0.0,0.0,5.0 deg. offset) | NEG_X to NSP
NEW WAYPOINT |  | 2016-125T20:09:00 |  | 000T12:35:00 | 2016-126T08:44:00 | ISS_NAC to Saturn (0.0,0.0,5.0 deg. offset) | NEG_X to NSP
VIMS_235SA_SPOLEMAP001_PRIME |  | 2016-125T20:09:00 |  | 000T01:00:00 | 2016-125T21:09:00 | ISS_NAC to Saturn | NEG_X to NSP
UVIS_235SA_AURSTARE001_PRIME | C, I, V | 2016-125T21:09:00 |  | 000T05:00:00 | 2016-126T02:09:00 | UVIS_FUV to Saturn | NEG_X to NSP | Collaborative Rider(s): VIMS
ISS_235SA_LIMBINT001_PRIME | C, U, V | 2016-126T02:09:00 |  | 000T02:00:00 | 2016-126T04:09:00 | ISS_NAC to Saturn | NEG_X to NSP
UVIS_235SA_AURSTARE002_PRIME | C, I, V | 2016-126T04:09:00 |  | 000T03:55:00 | 2016-126T08:04:00 | UVIS_FUV to Saturn | NEG_X to NSP | Collaborative Rider(s): VIMS
SP_235EA_DLTURN126_PRIME |  | 2016-126T08:04:00 |  | 000T00:07:00 | 2016-126T08:11:00 | ISS_NAC to Saturn (0.0,0.0,20.0 deg. offset) | NEG_X to NSP
SP_235EA_DLTURN426_PRIME |  | 2016-126T08:11:00 |  | 000T00:33:00 | 2016-126T08:44:00 | XBAND to Earth | NEG_X to NSP
NEW WAYPOINT |  | 2016-126T08:44:00 |  | 000T11:10:00 | 2016-126T19:54:00 | XBAND to Earth | NEG_X to NSP
SP_235EA_YGAP126_PRIME |  | 2016-126T08:44:00 |  | 000T01:30:00 | 2016-126T10:14:00 | XBAND to Earth | NEG_X to NSP
SP_235EA_C70METNON126_PRIME | C, R | 2016-126T10:14:00 |  | 000T09:00:00 | 2016-126T19:14:00 | XBAND to Earth | Rolling | CAPS.NEG_X to 40.6/83.5 (NSP) or NEP.
Titan Flyby T119 Segment |  | 2016-126T19:14:00 |  | 003T00:00:00 | 2016-129T19:14:00
SP_235TI_WAYPTTURN126_PRIME |  | 2016-126T19:14:00 |  | 000T00:40:00 | 2016-126T19:54:00 | NEG_Y to Titan | NEG_X to Sun
NEW WAYPOINT |  | 2016-126T19:54:00 |  | 001T14:20:00 | 2016-128T10:14:00 | NEG_Y to Titan | NEG_X to Sun
SP_235TI_DEADTIME126_PRIME |  | 2016-126T19:54:00 |  | 000T00:08:51 | 2016-126T20:02:51 | NEG_Y to Titan | NEG_X to Sun
CIRS_235TI_MIDIRTMAP001_PRIME | I, V | 2016-126T20:02:51 | GMB_E235_TITAN_T119-000T20:51:46 | 000T06:51:46 | 2016-127T02:54:37 | CIRS_FPB to Titan | PIC | Collaborative Rider(s): ISS
ISS_235TI_MONITORNA001_PRIME | C, U, V | 2016-127T02:54:37 | GMB_E235_TITAN_T119-000T14:00:00 | 000T02:00:00 | 2016-127T04:54:37 | ISS_NAC to Titan | NEG_X to Sun | No Preference to secondary pointing
CIRS_235TI_FIRNADCMP001_PRIME | I, U, V | 2016-127T04:54:37 | GMB_E235_TITAN_T119-000T12:00:00 | 000T03:00:00 | 2016-127T07:54:37 | CIRS_FP1 to Titan | PIC
CIRS_235TI_MIRLMBMAP001_PRIME | V | 2016-127T07:54:37 | GMB_E235_TITAN_T119-000T09:00:00 | 000T04:00:00 | 2016-127T11:54:37 | CIRS_FPB to Titan | PIC
Begin Custom Period |  | 2016-127T11:54:37 | GMB_E235_TITAN_T119-000T05:00:00 | 000T00:00:01 | 2016-127T11:54:38
CIRS_235TI_FIRNADMAP001_PRIME | V | 2016-127T11:54:37 | GMB_E235_TITAN_T119-000T05:00:00 | 000T02:42:00 | 2016-127T14:36:37 | CIRS_FP1 to Titan | NEG_Z to Earth | Pick up at NEG_Y to Titan, NEG_X to Sun; Hand off at NEG_Y to Titan, NEG_Z to Earth.
ENGR_235SC_ORSRCS127_PRIME | R | 2016-127T14:36:37 | GMB_E235_TITAN_T119-000T02:18:00 | 000T00:01:00 | 2016-127T14:37:37 | NEG_Y to Titan | NEG_Z to Earth | Pick up at NEG_Y to Titan, NEG_Z to Earth; Hand off at NEG_Y to Titan, NEG_Z to Earth. deadband = (0.5,2,0.5) for CIRS
CIRS_235TI_FIRLMBINT001_PRIME | I, M, R, V | 2016-127T14:37:37 | GMB_E235_TITAN_T119-000T02:17:00 | 000T01:02:00 | 2016-127T15:39:37 | CIRS_FP1 to Titan | NEG_Z to Earth | Collaborative Rider(s): MIMI. Pick up at NEG_Y to Titan, NEG_Z to Earth; Hand off at CIRS_FP1 to Titan, NEG_Z to Earth. Collaborative Rider(s): MIMI
CIRS_235TI_FIRLMBAER001_PRIME | M, R, V | 2016-127T15:39:37 | GMB_E235_TITAN_T119-000T01:15:00 | 000T00:30:00 | 2016-127T16:09:37 | CIRS_FP1 to Titan | NEG_Z to Earth | Collaborative Rider(s): MIMI. Pick up at CIRS_FP1 to Titan, NEG_Z to Earth; Hand off at CIRS_FP1 to Titan, NEG_Z to Earth. Collaborative Rider(s): MIMI
CIRS_235TI_FIRLMBT001_PRIME | M, R, V | 2016-127T16:09:37 | GMB_E235_TITAN_T119-000T00:45:00 | 000T00:30:00 | 2016-127T16:39:37 | CIRS_FP1 to Titan | NEG_Z to Earth | Collaborative Rider(s): MIMI. Pick up at CIRS_FP1 to Titan, NEG_Z to Earth; Hand off at NEG_X to Titan_SC_RAM, NEG_Z to Earth. Collaborative Rider(s): MIMI
Set deadband to (2,2,2) to ... |  | 2016-127T16:39:27 | GMB_E235_TITAN_T119-000T00:15:10 | 000T00:01:00 | 2016-127T16:40:27 |  |  | Deadband = (2.0, 2.0, 2.0)
INMS_235TI_TITAN119001_PRIME | C, M, R | 2016-127T16:39:37 | GMB_E235_TITAN_T119-000T00:15:00 | 000T00:23:39 | 2016-127T17:03:16 | NEG_X to Titan_SC_RAM | XBAND to Earth | Collaborative Rider(s): MIMI. Pick up at NEG_X to Titan_SC_RAM, NEG_Z to Earth; Hand off at XBAND to Earth (12.0,8.5,-6.5 deg. offset), NEG_X to Titan_SC_RAM. Collaborative Rider(s): MIMI. Use MIMI-preferred secondary NEG_Z to Earth
235TI (t) T119 TITAN Outbou... |  | 2016-127T16:54:37 |  | 000T00:00:01 | 2016-127T16:54:38
Set deadband to (0.5,0.5,2)... |  | 2016-127T17:03:06 | GMB_E235_TITAN_T119+000T00:08:29 | 000T00:01:00 | 2016-127T17:04:06 |  |  | Deadband = (0.5, 0.5, 2.0)
RSS_235TI_OCC001_PRIME | C, M | 2016-127T17:03:16 | LUB_E235_TITAN_T119+000T00:08:39 | 000T00:18:21 | 2016-127T17:21:37 | XBAND to Earth | NEG_X to Titan_SC_RAM | Collaborative Rider(s): MIMI. Pick up at XBAND to Earth (12.0,8.5,-6.5 deg. offset), NEG_X to Titan_SC_RAM; Hand off at XBAND to Earth, NEG_X to Titan_SC_RAM. Collaborative Rider(s): MIMI. RSS egress occultation of Titan's atmosphere
RSS_235TI_BISTATOUT001_PRIME | C, M | 2016-127T17:21:37 | LUB_E235_TITAN_T119+000T00:27:00 | 000T01:43:00 | 2016-127T19:04:37 | XBAND to Titan | PIC | Collaborative Rider(s): MIMI. Pick up at XBAND to Earth, NEG_X to Titan_SC_RAM; Hand off at NEG_Y to Titan, NEG_X to Sun. Collaborative Rider(s): MIMI. Egress bistatic surface scattering observation
End Custom Period |  | 2016-127T19:04:37 | GMB_E235_TITAN_T119+000T02:10:00 | 000T00:00:01 | 2016-127T19:04:38
ENGR_235SC_DFPWBIAS127_PPS | C, V | 2016-127T19:04:37 | GMB_E235_TITAN_T119+000T02:10:00 | 000T00:21:07 | 2016-127T19:25:44 |  |  | Deadband: (2,2,2).
VIMS_235TI_REGMAP001_PRIME | C, I | 2016-127T19:26:37 | GMB_E235_TITAN_T119+000T02:32:00 | 000T02:28:00 | 2016-127T21:54:37 | VIMS_IR to Titan | NEG_X to Sun | No Preference to secondary pointing
VIMS_235TI_MEDRES001_PRIME | C, I | 2016-127T21:54:37 | GMB_E235_TITAN_T119+000T05:00:00 | 000T04:00:00 | 2016-128T01:54:37 | VIMS_IR to Titan | NEG_X to Sun | Collaborative Rider(s): ISS. No Preference to secondary pointing
CIRS_235TI_FIRNADCMP002_PRIME | I, U, V | 2016-128T01:54:37 | GMB_E235_TITAN_T119+000T09:00:00 | 000T04:00:00 | 2016-128T05:54:37 | CIRS_FP1 to Titan | PIC
CIRS_235TI_MIDIRTMAP002_PRIME | I, V | 2016-128T05:54:37 | GMB_E235_TITAN_T119+000T13:00:00 | 000T03:24:23 | 2016-128T09:19:00 | CIRS_FPB to Titan | PIC
SP_235TI_DEADTIME128_PRIME |  | 2016-128T09:19:00 | GMB_E235_TITAN_T119+000T16:24:23 | 000T00:15:00 | 2016-128T09:34:00 | NEG_Y to Titan | NEG_X to Sun
SP_235EA_DLTURN128_PRIME |  | 2016-128T09:34:00 |  | 000T00:40:00 | 2016-128T10:14:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-128T10:14:00 |  | 000T09:40:00 | 2016-128T19:54:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
SP_235EA_C70METNON128_PRIME | C | 2016-128T10:14:00 |  | 000T09:00:00 | 2016-128T19:14:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | Rolling/SRU | MIMI.NEG_Y to Saturn (0,0,-9.5).SRU.
SP_235TI_WAYPTTURN128_PRIME |  | 2016-128T19:14:00 |  | 000T00:40:00 | 2016-128T19:54:00 | NEG_Y to Titan | NEG_X to NTP
NEW WAYPOINT |  | 2016-128T19:54:00 |  | 000T12:50:00 | 2016-129T08:44:00 | NEG_Y to Titan | NEG_X to NTP
ISS_235TI_CLOUD001_PRIME | V | 2016-128T19:54:00 |  | 000T04:00:00 | 2016-128T23:54:00 | ISS_NAC to Titan | NEG_X to NTP | No Preference to secondary pointing
ISS_235TI_CLOUD002_PRIME | V | 2016-128T23:54:00 |  | 000T04:10:00 | 2016-129T04:04:00 | ISS_NAC to Titan | NEG_X to NTP | No Preference to secondary pointing
ISS_235TI_CLOUD003_PRIME | V | 2016-129T04:04:00 |  | 000T01:00:00 | 2016-129T05:04:00 | ISS_NAC to Titan | NEG_X to NTP | No Preference to secondary pointing
RADAR_235TI_RADIOMCAL134_PRIME |  | 2016-129T05:04:00 |  | 000T02:00:00 | 2016-129T07:04:00 | NEG_Z to Titan | NEG_X to NTP | No Preference to secondary pointing
ISS_235TI_CLOUD004_PRIME | V | 2016-129T07:04:00 |  | 000T01:00:00 | 2016-129T08:04:00 | ISS_NAC to Titan | NEG_X to NTP | No Preference to secondary pointing
SP_235EA_DLTURN129_PRIME |  | 2016-129T08:04:00 |  | 000T00:40:00 | 2016-129T08:44:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-129T08:44:00 |  | 000T10:41:00 | 2016-129T19:25:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
SP_235EA_YGAP129_PRIME |  | 2016-129T08:44:00 |  | 000T01:30:00 | 2016-129T10:14:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
SP_235EA_C34BWGNON129_PRIME | C | 2016-129T10:14:00 |  | 000T09:00:00 | 2016-129T19:14:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | Rolling/SRU | MIMI.NEG_Y to Saturn (0,0,-9.5).SRU.
XD_235_236 Segment |  | 2016-129T19:14:00 |  | 025T22:01:00 | 2016-155T17:15:00
SP_235EA_DLTURN529_PRIME |  | 2016-129T19:14:00 |  | 000T00:11:00 | 2016-129T19:25:00 | XBAND to Earth | NEG_Y to 156.0/-17.0
NEW WAYPOINT |  | 2016-129T19:25:00 |  | 003T12:49:00 | 2016-133T08:14:00 | XBAND to Earth | NEG_Y to 156.0/-17.0
ISS_235RI_PHOEBEHOL001_PRIME | C, U, V | 2016-129T19:25:00 |  | 000T14:34:00 | 2016-130T09:59:00 | ISS_NAC to 242.0/-24.5 | PIC | Must point within 15 deg of NAC to 242/-24.5
SP_235EA_C34BWGOTP130_PRIME | C, E, N | 2016-130T09:59:00 |  | 000T09:00:00 | 2016-130T18:59:00 | XBAND to Earth | NEG_Y to 156.0/-17.0 | MIMI.RA/DEC for NEG_Y to Saturn (0,0,-9.5).OTP.SRU.post-TOST flyby.
ISS_235RF_FMOVIE002_PRIME | C, V | 2016-130T18:59:00 |  | 000T15:00:00 | 2016-131T09:59:00 | ISS_NAC to Rings | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
SP_235EA_C34HEFOTB131_PRIME | C, N | 2016-131T09:59:00 |  | 000T09:00:00 | 2016-131T18:59:00 | XBAND to Earth | 4_Hr_Rolling | MIMI.same secondary as OTP pass.OTB.SRU.
ISS_235OT_SKAPOL015_PRIME | U, V | 2016-131T18:59:00 |  | 001T13:05:00 | 2016-133T08:04:00 | UVIS_FUV to Rocks | NEG_X to NEP | JETTISON DAY. Must point at Skathi.
SP_235EA_DLTURN133_PRIME |  | 2016-133T08:04:00 |  | 000T00:10:00 | 2016-133T08:14:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
NEW WAYPOINT |  | 2016-133T08:14:00 |  | 000T11:46:00 | 2016-133T20:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_YGAP133_PRIME |  | 2016-133T08:14:00 |  | 000T01:30:00 | 2016-133T09:44:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_C70METNON133_PRIME | C | 2016-133T09:44:00 |  | 000T09:00:00 | 2016-133T18:44:00 | XBAND to Earth | Rolling/SRU | SRU.
SP_235SA_WAYPTTURN133_PRIME |  | 2016-133T19:20:00 |  | 000T00:40:00 | 2016-133T20:00:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
NEW WAYPOINT |  | 2016-133T20:00:00 |  | 001T10:40:00 | 2016-135T06:40:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
CIRS_235SA_MIRMAP003_PRIME | I, V | 2016-133T20:00:00 |  | 000T23:00:00 | 2016-134T19:00:00 | CIRS_FP3 to Saturn | POS_Z to NSP
CIRS_235RA_COMPLLRES002_PRIME | C, U, V | 2016-134T19:00:00 |  | 000T10:00:00 | 2016-135T05:00:00 | CIRS_FP1 to Rings | POS_Z to 190.7/59.7 | No Preference to secondary pointing. Must point withing 15 degrees of Saturn center
ISS_235OT_SATELLORB016_PRIME | C, I, V | 2016-135T05:00:00 |  | 000T01:00:00 | 2016-135T06:00:00 | ISS_NAC to Satellites | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
SP_235EA_DLTURN135_PRIME |  | 2016-135T06:00:00 |  | 000T00:40:00 | 2016-135T06:40:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
NEW WAYPOINT |  | 2016-135T06:40:00 |  | 005T05:45:00 | 2016-140T12:25:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_YGAP135_PRIME |  | 2016-135T08:14:00 |  | 000T01:30:00 | 2016-135T09:44:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_C34BWGNON135_PRIME | C | 2016-135T09:44:00 |  | 000T04:00:00 | 2016-135T13:44:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS Y BIASCAL. Secondary chosen for CDA.
ENGR_235SC_YBIASCAL001_AACS | C | 2016-135T13:44:00 |  | 000T01:30:00 | 2016-135T15:14:00 | POS_Z to DELTA_H | NEG_X to Sun
SP_235EA_C34BWG2ND135_PRIME | C | 2016-135T15:14:00 |  | 000T01:00:00 | 2016-135T16:14:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS Y BIASCAL. Secondary chosen for CDA.
ENGR_235SC_YBIASCAL002_AACS | C | 2016-135T16:14:00 |  | 000T01:30:00 | 2016-135T17:44:00 | POS_Z to DELTA_H | NEG_X to Sun
SP_235EA_C34BWG3RD135_PRIME | C | 2016-135T17:44:00 |  | 000T01:00:00 | 2016-135T18:44:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS Y BIASCAL. Secondary chosen for CDA.
SP_235EA_YGAP137_PRIME |  | 2016-137T08:00:00 |  | 000T01:30:00 | 2016-137T09:30:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_C70METNON137_PRIME | C | 2016-137T09:30:00 |  | 000T09:00:00 | 2016-137T18:30:00 | XBAND to Earth | Rolling/SRU | SRU.
ISS_235TI_M90R3CLD137_PRIME | C, V | 2016-137T18:30:00 | E235_M90R3CLD137+000T00:00:00 | 000T02:00:00 | 2016-137T20:30:00 | ISS_NAC to Titan | NEG_Z to 62.733/-29.802 | No Preference to secondary pointing
CDA_235DR_EXOGEN002_PRIME |  | 2016-137T20:30:00 |  | 000T09:00:00 | 2016-138T05:30:00 | XBAND to Earth | Rolling
CDA_235DR_EXOGEN006_PRIME |  | 2016-138T06:30:00 |  | 000T09:00:00 | 2016-138T15:30:00 | XBAND to Earth | Rolling
CDA_235DR_EXOGEN007_PRIME |  | 2016-138T16:30:00 |  | 000T09:00:00 | 2016-139T01:30:00 | XBAND to Earth | Rolling
SP_235EA_YGAP139_PRIME |  | 2016-139T02:00:00 |  | 000T01:30:00 | 2016-139T03:30:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_G34BWGNON139_PRIME | C, R | 2016-139T03:30:00 |  | 000T08:30:00 | 2016-139T12:00:00 | XBAND to Earth | Rolling/SRU | SRU.
CDA_235DR_EXOGEN008_PRIME |  | 2016-139T13:00:00 |  | 000T08:00:00 | 2016-139T21:00:00 | XBAND to Earth | Rolling
ENGR_235SC_KPTYBIAS140_PRIME |  | 2016-140T01:45:00 |  | 000T01:30:00 | 2016-140T03:15:00 | NEG_Z to DELTA_H (0.0,0.0,39.001 deg. offset) | NEG_X to Sun
SP_235EA_G34BWGNON140_PRIME | C, R | 2016-140T03:15:00 |  | 000T01:40:00 | 2016-140T04:55:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS 2 of 3 Rule and RSS Boresight. Secondary chosen for MIMI.
RSS_235EA_BORESIGHT002_PRIME | C, R | 2016-140T04:55:00 |  | 000T01:00:00 | 2016-140T05:55:00 | XBAND to Earth | PIC
SP_235EA_G34BWG2ND140_PRIME | C, R | 2016-140T05:55:00 |  | 000T05:50:00 | 2016-140T11:45:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS 2 of 3 Rule and RSS Boresight. Secondary chosen for MIMI.
SP_235SA_WAYPTTURN140_PRIME |  | 2016-140T11:45:00 |  | 000T00:40:00 | 2016-140T12:25:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
NEW WAYPOINT |  | 2016-140T12:25:00 |  | 000T03:10:00 | 2016-140T15:35:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
ISS_235TI_M60R3CLD140_PRIME | C, V | 2016-140T12:25:00 | E235_M60R3CLD140+000T00:00:00 | 000T01:30:00 | 2016-140T13:55:00 | ISS_NAC to Titan | NEG_X to 190.7/59.7 | No Preference to secondary pointing
ISS_235OT_SATELLORB020_PRIME | C, I, V | 2016-140T13:55:00 |  | 000T01:00:00 | 2016-140T14:55:00 | ISS_NAC to Satellites | NEG_X to 190.7/59.7 | Must point within 15 deg of Saturn Center
SP_235EA_DLTURN140_PRIME |  | 2016-140T14:55:00 |  | 000T00:40:00 | 2016-140T15:35:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
NEW WAYPOINT |  | 2016-140T15:35:00 |  | 001T20:50:00 | 2016-142T12:25:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
MAG_235SU_CALROLL002_PRIME | U | 2016-140T22:00:00 |  | 000T08:00:00 | 2016-141T06:00:00 | NEG_X to Earth (0.0,0.0,-30.0 deg. offset) | Rolling
SP_235EA_YGAP141_PRIME |  | 2016-141T06:00:00 |  | 000T01:30:00 | 2016-141T07:30:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_235EA_C70METNON141_PRIME | C | 2016-141T07:30:00 |  | 000T09:00:00 | 2016-141T16:30:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
Apoapse Per = 31.9 d, inc ... |  | 2016-141T13:11:34 |  | 000T00:00:01 | 2016-141T13:11:35
SP_236EA_YGAP142_PRIME |  | 2016-142T01:45:00 |  | 000T01:30:00 | 2016-142T03:15:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_236EA_G34BWGNON142_PRIME | C, R | 2016-142T03:15:00 |  | 000T08:30:00 | 2016-142T11:45:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
SP_236SA_WAYPTTURN142_PRIME |  | 2016-142T11:45:00 |  | 000T00:40:00 | 2016-142T12:25:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
NEW WAYPOINT |  | 2016-142T12:25:00 |  | 000T13:10:00 | 2016-143T01:35:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
ISS_236TI_M60R3CLD142_PRIME | C, V | 2016-142T12:25:00 | E236_M60R3CLD142+000T00:00:00 | 000T01:30:00 | 2016-142T13:55:00 | ISS_NAC to Titan | NEG_X to 190.7/59.7 | No Preference to secondary pointing
ISS_236OT_SATELLORB002_PRIME | C, I, V | 2016-142T13:55:00 |  | 000T01:00:00 | 2016-142T14:55:00 | ISS_NAC to Satellites | NEG_X to 190.7/59.7 | Must point within 15 deg of Saturn Center
CIRS_236RB_COMPLLRES001_PRIME | C, I, U, V | 2016-142T14:55:00 |  | 000T10:00:00 | 2016-143T00:55:00 | CIRS_FP1 to Rings | NEG_X to 190.7/59.7 | No Preference to secondary pointing. Must point within 15 degrees of Saturn center
SP_236EA_DLTURN143_PRIME |  | 2016-143T00:55:00 |  | 000T00:40:00 | 2016-143T01:35:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
NEW WAYPOINT |  | 2016-143T01:35:00 |  | 003T17:05:00 | 2016-146T18:40:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_236EA_C34HEFOTP143_PRIME | C, E, N | 2016-143T09:00:00 |  | 000T09:00:00 | 2016-143T18:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
SP_236EA_C34BWGOTB144_PRIME | C, N | 2016-144T09:00:00 |  | 000T09:00:00 | 2016-144T18:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
SP_236EA_YGAP146_PRIME |  | 2016-146T07:30:00 |  | 000T01:30:00 | 2016-146T09:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
SP_236EA_C34BWGNON146_PRIME | C, R | 2016-146T09:00:00 |  | 000T09:00:00 | 2016-146T18:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
SP_236SA_WAYPTTURN146_PRIME |  | 2016-146T18:00:00 |  | 000T00:40:00 | 2016-146T18:40:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
NEW WAYPOINT |  | 2016-146T18:40:00 |  | 001T23:20:00 | 2016-148T18:00:00 | ISS_NAC to Saturn | NEG_X to 190.7/59.7
ISS_236TI_M60R3CLD146_PRIME | C, V | 2016-146T18:40:00 | E236_M60R3CLD146+000T00:00:00 | 000T01:30:00 | 2016-146T20:10:00 | ISS_NAC to Titan | NEG_X to Sun
ISS_236OT_SATELLORB005_PRIME | C, I, V | 2016-146T20:10:00 |  | 000T01:00:00 | 2016-146T21:10:00 | ISS_NAC to Satellites | NEG_X to 190.7/59.7 | Must point within 15 deg of Saturn Center
ISS_236OT_ALBPOL121_PRIME | I, V | 2016-146T21:10:00 |  | 001T04:30:00 | 2016-148T01:40:00 | UVIS_FUV to Rocks | NEG_Z to NSP | JETTISON observation; must point at Albiorix.
VIMS_236RI_WHYAOCC001_PRIME | C | 2016-148T01:40:00 |  | 000T10:20:00 | 2016-148T12:00:00 | VIMS_IR to 207.261/-28.368 | NEG_X to 190.7/59.7 | Must point within 15 degrees of Saturn center
CIRS_236RI_SATREFL001_PRIME | C, U | 2016-148T12:00:00 |  | 000T05:20:00 | 2016-148T17:20:00 | CIRS_FP1 to Rings | NEG_X to 190.7/59.7 | No Preference to secondary pointing
SP_236EA_DLTURN148_PRIME |  | 2016-148T17:20:00 |  | 000T00:40:00 | 2016-148T18:00:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
NEW WAYPOINT |  | 2016-148T18:00:00 |  | 000T09:45:00 | 2016-149T03:45:00 | XBAND to Earth | NEG_Y to 157.7/-13.5
ENGR_236SC_KPTYBIAS148_PRIME |  | 2016-148T18:00:00 |  | 000T01:30:00 | 2016-148T19:30:00 | POS_Z to DELTA_H (0.0,0.0,90.006 deg. offset) | NEG_X to Sun
SP_236EA_M70METNON148_PRIME | C | 2016-148T19:30:00 |  | 000T07:45:00 | 2016-149T03:15:00 | XBAND to Earth | NEG_Y to 157.7/-13.5 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for MIMI.
SP_236SA_WAYPTTURN149_PRIME |  | 2016-149T03:15:00 |  | 000T00:30:00 | 2016-149T03:45:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
NEW WAYPOINT |  | 2016-149T03:45:00 |  | 001T14:00:00 | 2016-150T17:45:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
ISS_236OT_SATELLORB006_PRIME | C, I, V | 2016-149T03:45:00 |  | 000T00:45:00 | 2016-149T04:30:00 | ISS_NAC to Satellites | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
CIRS_236SA_COMPSIT003_PRIME | V | 2016-149T04:30:00 |  | 000T23:00:00 | 2016-150T03:30:00 | CIRS_FP3 to Saturn | POS_Z to 190.7/59.7
NAV_236SK_OPNAV501_PRIME |  | 2016-150T03:30:00 |  | 000T01:30:00 | 2016-150T05:00:00 | ISS_NAC to Satellites | POS_Z to 190.7/59.7 | No Preference to secondary pointing. Starts at waypoint, ends at same waypoint
CIRS_236RA_COMPLLRES001_PRIME | C, I, U, V | 2016-150T05:00:00 |  | 000T10:00:00 | 2016-150T15:00:00 | CIRS_FP1 to Rings | POS_Z to 190.7/59.7 | No Preference to secondary pointing. Must point within 15 degrees of Saturn center
UVIS_236TE_ICYLON001_PRIME | V | 2016-150T15:00:00 |  | 000T02:15:00 | 2016-150T17:15:00 | UVIS_FUV to Tethys (0.115,0.0,0.0 deg. offset) | POS_Z to 190.7/59.7 | Must point within 15 deg of RA/DEC
SP_236EA_DLTURN150_PRIME |  | 2016-150T17:15:00 |  | 000T00:30:00 | 2016-150T17:45:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
NEW WAYPOINT |  | 2016-150T17:45:00 |  | 001T09:55:00 | 2016-152T03:40:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
SP_236EA_YGAP150_PRIME |  | 2016-150T17:45:00 |  | 000T01:30:00 | 2016-150T19:15:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
SP_236EA_M34BWGNON150_PRIME | C | 2016-150T19:15:00 |  | 000T08:00:00 | 2016-151T03:15:00 | XBAND to Earth | Rolling
ISS_236RI_ARCORBIT001_PRIME | C, U, V | 2016-151T03:15:00 |  | 000T14:30:00 | 2016-151T17:45:00 | ISS_NAC to Rings (0.038,-65.0,-0.011 deg. offset) | NEG_X to 190.7/59.7 | Must point within 15 deg of Saturn Center
SP_236EA_YGAP151_PRIME |  | 2016-151T17:45:00 |  | 000T01:30:00 | 2016-151T19:15:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
SP_236EA_M70METNON151_PRIME | C | 2016-151T19:15:00 |  | 000T07:45:00 | 2016-152T03:00:00 | XBAND to Earth | Rolling
SP_236SA_WAYPTTURN152_PRIME |  | 2016-152T03:00:00 |  | 000T00:40:00 | 2016-152T03:40:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
NEW WAYPOINT |  | 2016-152T03:40:00 |  | 000T14:05:00 | 2016-152T17:45:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
ISS_236TI_M60R3CLD152_PRIME | C, V | 2016-152T03:40:00 | E236_M60R3CLD152+000T00:00:00 | 000T01:30:00 | 2016-152T05:10:00 | ISS_NAC to Titan | POS_Z to 190.7/59.7 | No Preference to secondary pointing
ISS_236OT_SATELLORB008_PRIME | C, I, V | 2016-152T05:10:00 |  | 000T01:00:00 | 2016-152T06:10:00 | ISS_NAC to Satellites | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
UVIS_236TE_ICYLON004_PRIME | V | 2016-152T06:10:00 |  | 000T04:50:00 | 2016-152T11:00:00 | UVIS_FUV to Tethys (0.115,0.0,0.0 deg. offset) | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
VIMS_236RI_APOMOSAIC001_PRIME | C, U | 2016-152T11:00:00 |  | 000T06:00:00 | 2016-152T17:00:00 | VIMS_IR to Rings | POS_Z to 190.7/59.7 | Must point within 15 degrees of Saturn center
SP_236EA_DLTURN152_PRIME |  | 2016-152T17:00:00 |  | 000T00:45:00 | 2016-152T17:45:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
NEW WAYPOINT |  | 2016-152T17:45:00 |  | 000T09:45:00 | 2016-153T03:30:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
ENGR_236SC_RWABIAS152_PRIME |  | 2016-152T17:45:00 |  | 000T01:30:00 | 2016-152T19:15:00 | XBAND to Earth | NEG_Y to 160.0/-5.5
SP_236EA_M34BWGNON152_PRIME | C, R | 2016-152T19:15:00 |  | 000T07:45:00 | 2016-153T03:00:00 | XBAND to Earth | Rolling
SP_236SA_WAYPTTURN153_PRIME |  | 2016-153T03:00:00 |  | 000T00:30:00 | 2016-153T03:30:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
NEW WAYPOINT |  | 2016-153T03:30:00 |  | 001T03:15:00 | 2016-154T06:45:00 | ISS_NAC to Saturn | POS_Z to 190.7/59.7
ISS_236TI_M60R3CLD153_PRIME | C, V | 2016-153T03:30:00 | E236_M60R3CLD153+000T00:00:00 | 000T01:30:00 | 2016-153T05:00:00 | ISS_NAC to Titan | POS_Z to 190.7/59.7 | No Preference to secondary pointing
ISS_236OT_SATELLORB009_PRIME | C, I, V | 2016-153T05:00:00 |  | 000T00:50:00 | 2016-153T05:50:00 | ISS_NAC to Satellites | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
UVIS_236ST_URDELSCO001_PRIME | C | 2016-153T05:50:00 |  | 000T09:00:00 | 2016-153T14:50:00 | UVIS_HSP to 240.083/-22.622 | POS_Z to 190.7/59.7 | Must point within 15 deg of Saturn Center
UVIS_236RH_LOPHASE001_PRIME | I, V | 2016-153T14:50:00 |  | 000T15:20:00 | 2016-154T06:10:00 | UVIS_FUV to Rhea (0.115,0.0,0.0 deg. offset) | POS_X to 63.0/-70.0 | Must point within 15 deg of Saturn Center
SP_236EA_DLTURN154_PRIME |  | 2016-154T06:10:00 |  | 000T00:35:00 | 2016-154T06:45:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-154T06:45:00 |  | 000T11:15:00 | 2016-154T18:00:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
SP_236EA_YGAP154_PRIME |  | 2016-154T06:45:00 |  | 000T01:30:00 | 2016-154T08:15:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
SP_236EA_C34BWGNON154_PRIME | C | 2016-154T08:15:00 |  | 000T09:00:00 | 2016-154T17:15:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | Rolling | MIMI.NEG_Y to Saturn (0,0,-9.5).
SP_236SA_WAYPTTURN154_PRIME |  | 2016-154T17:15:00 |  | 000T00:45:00 | 2016-154T18:00:00 | ISS_NAC to Saturn | NEG_Z to 190.7/59.7
NEW WAYPOINT |  | 2016-154T18:00:00 |  | 000T12:45:00 | 2016-155T06:45:00 | ISS_NAC to Saturn | NEG_Z to 190.7/59.7
CIRS_236RB_COMPLITB1001_PRIME | C, I, U, V | 2016-154T18:00:00 |  | 000T06:00:00 | 2016-155T00:00:00 | CIRS_FP1 to Rings | NEG_Z to 190.7/59.7 | No Preference to secondary pointing. Must point within 15 degrees of Saturn center
UVIS_236DI_LOPHASE001_PIE | C, I, V | 2016-155T00:00:00 |  | 000T06:15:00 | 2016-155T06:15:00 | UVIS_FUV to Dione (0.115,0.0,0.0 deg. offset) | NEG_Z to 190.7/59.7 | Collaborative Rider(s): ISS. Collaborative Rider(s): ISS
SP_236EA_DLTURN155_PRIME |  | 2016-155T06:15:00 |  | 000T00:30:00 | 2016-155T06:45:00 | XBAND to Earth | NEG_Y to 329.2/29.8
NEW WAYPOINT |  | 2016-155T06:45:00 |  | 000T11:10:00 | 2016-155T17:55:00 | XBAND to Earth | NEG_Y to 329.2/29.8
SP_236EA_YGAP155_PRIME |  | 2016-155T06:45:00 |  | 000T01:30:00 | 2016-155T08:15:00 | XBAND to Earth | NEG_Y to 329.2/29.8
SP_236EA_C70METNON155_PRIME | C, R | 2016-155T08:15:00 |  | 000T09:00:00 | 2016-155T17:15:00 | XBAND to Earth | Rolling
MAPS_236 Segment |  | 2016-155T17:15:00 |  | 003T09:30:00 | 2016-159T02:45:00
SP_236EA_WAYPTTURN155_PRIME |  | 2016-155T17:15:00 |  | 000T00:40:00 | 2016-155T17:55:00 | XBAND to Earth | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-155T17:55:00 |  | 001T00:00:00 | 2016-156T17:55:00 | XBAND to Earth | NEG_Y to Saturn
Begin Custom Period |  | 2016-155T17:55:00 |  | 000T00:00:01 | 2016-155T17:55:01
CIRS_236RH_COMPGLBL001_PRIME | C, I | 2016-155T17:55:00 |  | 000T07:05:00 | 2016-156T01:00:00 | CIRS_FP1 to Rhea | NEG_X to 179.7/38.0 | Collaborative Rider(s): ISS. Pick up at XBAND to Earth, NEG_Y to Saturn; Hand off at ISS_NAC to Titan, NEG_X to 142.802/44.18. Collaborative Rider(s): ISS
ISS_236TI_M30R2CLD155_PRIME | C, V | 2016-156T01:00:00 | E236_M30R2CLD155+000T00:00:00 | 000T01:30:00 | 2016-156T02:30:00 | ISS_NAC to Titan | NEG_X to 142.802/44.18 | Pick up at ISS_NAC to Titan, NEG_X to 142.802/44.18; Hand off at XBAND to Earth, NEG_Y to Saturn.
End Custom Period |  | 2016-156T02:30:00 |  | 000T00:00:01 | 2016-156T02:30:01
CDA_236DR_RPX1100002_PRIME | M | 2016-156T02:30:00 |  | 000T05:45:00 | 2016-156T08:15:00 | NEG_Z to Earth | NEG_X to NSP
SP_236EA_C34BWGOTP156_PRIME | C, E, N | 2016-156T08:15:00 |  | 000T09:00:00 | 2016-156T17:15:00 | XBAND to Earth | 4_Hr_Rolling | MAPS/CAPS.update during integration.OTP.SRU.
SP_236SA_WAYPTTURN156_PRIME |  | 2016-156T17:15:00 |  | 000T00:40:00 | 2016-156T17:55:00 | NEG_Y to Saturn | NEG_X to NSP
NEW WAYPOINT |  | 2016-156T17:55:00 |  | 000T14:20:00 | 2016-157T08:15:00 | NEG_Y to Saturn | NEG_X to NSP
ISS_236TI_M60R2CLD156_PRIME | C, V | 2016-156T17:55:00 | E236_M60R2CLD156+000T00:00:00 | 000T01:30:00 | 2016-156T19:25:00 | ISS_NAC to Titan | NEG_X to 353.619/50.393
UVIS_236SA_ENAURFOOT001_PIE | C, V | 2016-156T19:25:00 |  | 000T12:10:00 | 2016-157T07:35:00 | UVIS_FUV to Saturn | NEG_X to NSP | Collaborative Rider(s): VIMS
SP_236EA_DLTURN157_PRIME |  | 2016-157T07:35:00 |  | 000T00:40:00 | 2016-157T08:15:00 | XBAND to Earth | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-157T08:15:00 |  | 000T09:40:00 | 2016-157T17:55:00 | XBAND to Earth | NEG_Y to Saturn
SP_236EA_C70METOTB157_PRIME | C, N | 2016-157T08:15:00 |  | 000T09:00:00 | 2016-157T17:15:00 | XBAND to Earth | 4_Hr_Rolling | MAPS/CAPS.same secondary as OTP pass.OTB.SRU.
Periapse R = 10.039 Rs, lat... |  | 2016-157T11:45:42 |  | 000T00:00:01 | 2016-157T11:45:43
SP_236SA_WAYPTTURN157_PRIME |  | 2016-157T17:15:00 |  | 000T00:40:00 | 2016-157T17:55:00 | NEG_Y to Saturn (0.0,15.0,0.0 deg. offset) | NEG_X to NSP
NEW WAYPOINT |  | 2016-157T17:55:00 |  | 000T09:40:00 | 2016-158T03:35:00 | NEG_Y to Saturn (0.0,15.0,0.0 deg. offset) | NEG_X to NSP
UVIS_236SA_AURSLEW001_PRIME | C, R, V | 2016-157T17:55:00 |  | 000T09:00:00 | 2016-158T02:55:00 | UVIS_FUV to Saturn | NEG_X to NSP | Collaborative Rider(s): VIMS
SP_236EA_WAYPTTURN158_PRIME | R | 2016-158T02:55:00 |  | 000T00:30:00 | 2016-158T03:25:00 | NEG_Z to Saturn (0.0,0.0,20.0 deg. offset) | POS_Y to NSP
SP_236EA_WAYPTTURN458_PRIME | R | 2016-158T03:25:00 |  | 000T00:10:00 | 2016-158T03:35:00 | XBAND to Earth | POS_Y to NSP
NEW WAYPOINT |  | 2016-158T03:35:00 |  | 000T23:50:00 | 2016-159T03:25:00 | XBAND to Earth | POS_Y to NSP
RSS_236RI_OCC001_PIE |  | 2016-158T03:35:00 |  | 000T07:26:00 | 2016-158T11:01:00 | XBAND to Earth | PIC
MAG_236SU_CALROLL001_PRIME | U | 2016-158T11:01:00 |  | 000T06:14:00 | 2016-158T17:15:00 | NEG_X to Earth (0.0,0.0,-30.0 deg. offset) | Rolling
ENGR_236SC_KPTYBIAS158_PRIME |  | 2016-158T17:15:00 |  | 000T01:30:00 | 2016-158T18:45:00 | NEG_Z to DELTA_H (0.0,0.0,34.003 deg. offset) | NEG_X to Sun
SP_236EA_M70METNON158_PRIME | C | 2016-158T18:45:00 |  | 000T08:00:00 | 2016-159T02:45:00 | XBAND to Earth | Rolling | MIMI. WP attitude is XBand to EA, POS_Y to NSP. Turn to T120 following segment works from this attitude.
Titan Flyby T120 Segment |  | 2016-159T02:45:00 |  | 002T07:45:00 | 2016-161T10:30:00
SP_236TI_WAYPTTURN159_PRIME |  | 2016-159T02:45:00 |  | 000T00:40:00 | 2016-159T03:25:00 | NEG_Y to Titan | NEG_X to NTP
NEW WAYPOINT |  | 2016-159T03:25:00 |  | 001T04:35:00 | 2016-160T08:00:00 | NEG_Y to Titan | NEG_X to NTP
SP_236TI_DEADTIME159_PRIME |  | 2016-159T03:25:00 |  | 000T00:08:39 | 2016-159T03:33:39
CIRS_236TI_FIRNADCMP001_PRIME | I, U, V | 2016-159T03:33:39 | GMB_E236_TITAN_T120-000T10:32:38 | 000T01:32:38 | 2016-159T05:06:17 | CIRS_FP1 to Titan | PIC
Begin custom period |  | 2016-159T03:39:59 | GMB_E236_TITAN_T120-000T10:26:18 | 000T00:00:01 | 2016-159T03:40:00
CIRS_236TI_MIRLMBINT001_PRIME | I, V | 2016-159T05:06:17 | GMB_E236_TITAN_T120-000T09:00:00 | 000T04:00:00 | 2016-159T09:06:17 | CIRS_FPB to Titan | PIC | Pick up at NEG_Y to Titan, NEG_X to NTP; Hand off at CIRS_FP1 to Titan, NEG_X to NTP.
CIRS_236TI_FIRNADMAP001_PRIME | V | 2016-159T09:06:17 | GMB_E236_TITAN_T120-000T05:00:00 | 000T02:30:00 | 2016-159T11:36:17 | CIRS_FP1 to Titan | PIC | Pick up at CIRS_FP1 to Titan, NEG_X to NTP; Hand off at CIRS_FP1 to Titan, NEG_X to NTP.
CIRS_236TI_FIRLMBINT001_PRIME | I, M, V | 2016-159T11:36:17 | GMB_E236_TITAN_T120-000T02:30:00 | 000T01:15:00 | 2016-159T12:51:17 | CIRS_FP1 to Titan | PIC | Pick up at CIRS_FP1 to Titan, NEG_X to NTP; Hand off at CIRS_FP1 to Titan, PIC. Handoff at CIRS_FP1 to Titan, Lat_View, 51S, 90 degrees, LHS, 225 km altitude; POS_Z to Titan FOV_Limb, 51S, LHS
ENGR_236SC_RADRCS159_PRIME | M | 2016-159T12:51:17 | GMB_E236_TITAN_T120-000T01:15:00 | 000T00:01:00 | 2016-159T12:52:17 | CIRS_FP1 to Titan | PIC | Pick up at CIRS_FP1 to Titan, PIC; Hand off at CIRS_FP1 to Titan, PIC. Deadband = (0.5,2.0,0.5)
CIRS_236TI_FIRLMBAER002_PRIME | M, V | 2016-159T12:52:17 | GMB_E236_TITAN_T120-000T01:14:00 | 000T00:44:00 | 2016-159T13:36:17 | CIRS_FP1 to Titan | PIC | Pick up at CIRS_FP1 to Titan, PIC; Hand off at NEG_Z to Titan, NEG_X to NTP. Pickup at CIRS_FP1 to Titan, Lat_View, 51S, 90 degrees, LHS, 225 km altitude; POS_Z to Titan FOV_Limb, 51S, LHS. Handoff at NEG_Z to Titan, NEG_X to NTP.
Switch from (0.5,2,0.5) for... |  | 2016-159T13:35:17 | GMB_E236_TITAN_T120-000T00:31:00 | 000T00:01:00 | 2016-159T13:36:17 |  |  | Deadband = (0.5, 0.5, 2.0)
RADAR_236TI_T120INALT001_PRIME | M | 2016-159T13:36:17 | GMB_E236_TITAN_T120-000T00:30:00 | 000T00:12:00 | 2016-159T13:48:17 | NEG_Z to Titan | NEG_X to Titan_SC_RAM | Pick up at NEG_Z to Titan, NEG_X to NTP; Hand off at NEG_Z to Titan, NEG_X to Titan_SC_RAM.
Begin Dual Playback Science |  | 2016-159T13:48:17 | GMB_E236_TITAN_T120-000T00:18:00 | 000T00:00:01 | 2016-159T13:48:18
RADAR_236TI_T120INSAR001_PRIME | M | 2016-159T13:48:17 | GMB_E236_TITAN_T120-000T00:18:00 | 000T00:18:00 | 2016-159T14:06:17 | NEG_Z to Titan | NEG_X to Titan_SC_RAM | Pick up at NEG_Z to Titan, NEG_X to Titan_SC_RAM; Hand off at NEG_X to Titan_SC_RAM, NEG_Z to Titan. INMS ride along.
236TI (t) T120 TITAN Outbou... |  | 2016-159T14:06:17 |  | 000T00:00:01 | 2016-159T14:06:18
RADAR_236TI_T120OTRAS001_PRIME | M | 2016-159T14:06:17 | GMB_E236_TITAN_T120+000T00:00:00 | 000T00:15:00 | 2016-159T14:21:17 | NEG_X to Titan_SC_RAM | NEG_Z to Titan | Collaborative Rider(s): INMS. Pick up at NEG_X to Titan_SC_RAM, NEG_Z to Titan; Hand off at NEG_X to Titan_SC_RAM, NEG_Z to Titan. Collaborative Rider(s): INMS. Ride-along at c/a.
End Dual Playback Science |  | 2016-159T14:21:17 | GMB_E236_TITAN_T120+000T00:15:00 | 000T00:00:01 | 2016-159T14:21:18
RADAR_236TI_T120OTALT001_PRIME | M | 2016-159T14:21:17 | GMB_E236_TITAN_T120+000T00:15:00 | 000T00:15:00 | 2016-159T14:36:17 | NEG_Z to Titan | NEG_Y to NTP | Pick up at NEG_X to Titan_SC_RAM, NEG_Z to Titan; Hand off at NEG_Z to Titan, NEG_Y to NTP.
ENGR_236SC_RADRWBIAS159_PPS | M | 2016-159T14:36:17 | GMB_E236_TITAN_T120+000T00:30:00 | 000T00:22:00 | 2016-159T14:58:17 | NEG_Z to Titan | NEG_Y to NTP | Pick up at NEG_Z to Titan, NEG_Y to NTP; Hand off at NEG_Z to Titan, NEG_Y to NTP.
RADAR_236TI_T120OHSAR001_PRIME | M | 2016-159T14:58:17 | GMB_E236_TITAN_T120+000T00:52:00 | 000T00:45:00 | 2016-159T15:43:17 | NEG_Z to Titan | NEG_Y to NTP | Pick up at NEG_Z to Titan, NEG_Y to NTP; Hand off at NEG_Z to Titan, NEG_Y to NTP.
RADAR_236TI_T120OTSCT001_PRIME | M | 2016-159T15:43:17 | GMB_E236_TITAN_T120+000T01:37:00 | 000T00:38:00 | 2016-159T16:21:17 | NEG_Z to Titan | NEG_Y to NTP | Pick up at NEG_Z to Titan, NEG_Y to NTP; Hand off at NEG_Y to Titan, NEG_X to NTP.
End custom period |  | 2016-159T16:21:17 | GMB_E236_TITAN_T120+000T02:15:00 | 000T00:00:01 | 2016-159T16:21:18
CIRS_236TI_FIRNADMAP002_PRIME | V | 2016-159T16:21:17 | GMB_E236_TITAN_T120+000T02:15:00 | 000T02:45:00 | 2016-159T19:06:17 | CIRS_FP1 to Titan | PIC
CIRS_236TI_MIRLMBMAP002_PRIME | V | 2016-159T19:06:17 | GMB_E236_TITAN_T120+000T05:00:00 | 000T04:00:00 | 2016-159T23:06:17 | CIRS_FPB to Titan | PIC
CIRS_236TI_FIRNADCMP002_PRIME | I, U, V | 2016-159T23:06:17 | GMB_E236_TITAN_T120+000T09:00:00 | 000T04:00:00 | 2016-160T03:06:17 | CIRS_FP1 to Titan | PIC
CIRS_236TI_MIDIRTMAP002_PRIME | I, V | 2016-160T03:06:17 | GMB_E236_TITAN_T120+000T13:00:00 | 000T03:52:22 | 2016-160T06:58:39 | CIRS_FPB to Titan | PIC | Template
SP_236TI_DEADTIME160_PRIME |  | 2016-160T06:58:39 | GMB_E236_TITAN_T120+000T16:52:22 | 000T00:21:20 | 2016-160T07:19:59 | NEG_Y to Titan
SP_236EA_DLTURN160_PRIME |  | 2016-160T07:20:00 |  | 000T00:40:00 | 2016-160T08:00:00 | XBAND to Earth | NEG_Y to 153.0/-20.0
NEW WAYPOINT |  | 2016-160T08:00:00 |  | 000T09:40:00 | 2016-160T17:40:00 | XBAND to Earth | NEG_Y to 153.0/-20.0
SP_236EA_C70METNON160_PRIME | C | 2016-160T08:00:00 |  | 000T09:00:00 | 2016-160T17:00:00 | XBAND to Earth | NEG_Y to 153.0/-20.0 | MIMI.NEG_Y to Saturn (0,0,-9.5).SRU.post-TOST flyby.
Pointer Reset in preparatio... |  | 2016-160T17:00:00 |  | 000T01:00:00 | 2016-160T18:00:00
SP_236TI_WAYPTTURN160_PRIME |  | 2016-160T17:00:00 |  | 000T00:40:00 | 2016-160T17:40:00 | NEG_Y to Titan | NEG_X to NSP
NEW WAYPOINT |  | 2016-160T17:40:00 |  | 000T06:35:00 | 2016-161T00:15:00 | NEG_Y to Titan | NEG_X to NSP
ISS_236TI_CLOUD001_PRIME | C, V | 2016-160T17:40:00 |  | 000T02:55:00 | 2016-160T20:35:00 | ISS_NAC to Titan | NEG_X to NSP | No Preference to secondary pointing
ISS_236TI_CLOUD002_PRIME | C, V | 2016-160T20:35:00 |  | 000T02:00:00 | 2016-160T22:35:00 | ISS_NAC to Titan | NEG_X to NSP | No Preference to secondary pointing
ISS_236TI_CLOUD003_PRIME | C, V | 2016-160T22:35:00 |  | 000T01:00:00 | 2016-160T23:35:00 | ISS_NAC to Titan | NEG_X to NSP | No Preference to secondary pointing
SP_236EA_DLTURN460_PRIME |  | 2016-160T23:35:00 |  | 000T00:40:00 | 2016-161T00:15:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
NEW WAYPOINT |  | 2016-161T00:15:00 |  | 000T10:35:00 | 2016-161T10:50:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | NEG_Y to Saturn
ENGR_236SC_KPTYBIAS161_PRIME |  | 2016-161T00:15:00 |  | 000T01:30:00 | 2016-161T01:45:00 | NEG_Z to DELTA_H (0.0,0.0,-82.002 deg. offset) | NEG_X to Sun
SP_236EA_G70METNON161_PRIME | C | 2016-161T01:45:00 |  | 000T08:45:00 | 2016-161T10:30:00 | XBAND to Earth (0.0,0.0,-9.5 deg. offset) | Rolling/SRU | MIMI.NEG_Y to Saturn (0,0,-9.5).SRU.
XD_236_237 Segment |  | 2016-161T10:30:00 |  | 017T05:14:00 | 2016-178T15:44:00
SP_236SA_WAYPTTURN161_PRIME |  | 2016-161T10:30:00 |  | 000T00:20:00 | 2016-161T10:50:00 | ISS_NAC to Saturn | NEG_X to NSP
NEW WAYPOINT |  | 2016-161T10:50:00 |  | 000T13:25:00 | 2016-162T00:15:00 | ISS_NAC to Saturn | NEG_X to NSP
ISS_236OT_SATELLORB011_PRIME | C, V | 2016-161T10:50:00 |  | 000T01:00:00 | 2016-161T11:50:00 | ISS_NAC to Satellites | NEG_X to NSP | Must point within 15 deg of Saturn Center
CIRS_236SA_FIRMAP002_PRIME | V | 2016-161T11:50:00 |  | 000T12:00:00 | 2016-161T23:50:00 | CIRS_FP1 to Saturn | NEG_X to NSP
SP_236EA_DLTURN161_PRIME |  | 2016-161T23:50:00 |  | 000T00:25:00 | 2016-162T00:15:00 | XBAND to Earth | NEG_X to 141.0/-42.0
NEW WAYPOINT |  | 2016-162T00:15:00 |  | 000T10:20:00 | 2016-162T10:35:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_236EA_YGAP162_PRIME |  | 2016-162T00:15:00 |  | 000T01:30:00 | 2016-162T01:45:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_236EA_G34BWGNON162_PRIME | C, R | 2016-162T01:45:00 |  | 000T08:30:00 | 2016-162T10:15:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 141/-42.SRU.
SP_236SA_WAYPTTURN162_PRIME |  | 2016-162T10:15:00 |  | 000T00:20:00 | 2016-162T10:35:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
NEW WAYPOINT |  | 2016-162T10:35:00 |  | 000T21:10:00 | 2016-163T07:45:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
ISS_236TI_M120R2HZ162_PRIME | C, I, V | 2016-162T10:35:00 | E236_M120R2HZ162+000T00:00:00 | 000T01:30:00 | 2016-162T12:05:00 | ISS_NAC to Titan | NEG_X to 191.4/52.8 | No Preference to secondary pointing
ISS_236RF_FMOVIE002_PRIME | C, I, V | 2016-162T12:05:00 |  | 000T15:00:00 | 2016-163T03:05:00 | ISS_NAC to Rings | NEG_X to 191.4/52.8 | Must point within 15 deg of Saturn Center
ISS_236RI_COLPHMEMP001_PRIME | C, U, V | 2016-163T03:05:00 |  | 000T04:20:00 | 2016-163T07:25:00 | ISS_NAC to Rings | NEG_X to NSP | Must point within 15 deg of Saturn Center
SP_236EA_DLTURN163_PRIME |  | 2016-163T07:25:00 |  | 000T00:20:00 | 2016-163T07:45:00 | XBAND to Earth | NEG_X to 141.0/-42.0
NEW WAYPOINT |  | 2016-163T07:45:00 |  | 007T09:00:00 | 2016-170T16:45:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_236EA_C34BWGOTP163_PRIME | C, E, N | 2016-163T07:45:00 |  | 000T09:00:00 | 2016-163T16:45:00 | XBAND to Earth | 4_Hr_Rolling | CDA.NEG_X to 141/-42.OTP.SRU.
ISS_236OT_TAQROTA037_PRIME | M, U, V | 2016-163T16:45:00 |  | 000T15:00:00 | 2016-164T07:45:00 | UVIS_FUV to Rocks | NEG_X to 109.945/68.998 | Collaborative Rider(s): CDA. Must point within 15 deg of 233/9
SP_236EA_C34BWGOTB164_PRIME | C, N | 2016-164T07:45:00 |  | 000T09:00:00 | 2016-164T16:45:00 | XBAND to Earth | 4_Hr_Rolling | CDA.same secondary as OTP pass.OTB.SRU.
ISS_236OT_TAQROTB036_PRIME | M, U, V | 2016-164T16:45:00 |  | 001T13:15:00 | 2016-166T06:00:00 | UVIS_FUV to Rocks | NEG_X to 129.055/62.502 | Collaborative Rider(s): CDA. Must point within 15 deg of 233/9
SP_236EA_YGAP166_PRIME |  | 2016-166T06:00:00 |  | 000T01:30:00 | 2016-166T07:30:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_236EA_C70METSEQ166_PRIME | C | 2016-166T07:30:00 |  | 000T09:00:00 | 2016-166T16:30:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 141/-42.SRU.
SP_236EA_YGAP168_PRIME |  | 2016-168T06:00:00 |  | 000T01:30:00 | 2016-168T07:30:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_236EA_C34BWGSEQ168_PRIME | C, E, R | 2016-168T07:30:00 |  | 000T09:00:00 | 2016-168T16:30:00 | XBAND to Earth | Rolling/SRU | CDA.NEG_X to 141/-42.SRU.
ISS_236OT_TAQROTD033_PRIME | M, U, V | 2016-168T16:30:00 |  | 001T13:15:00 | 2016-170T05:45:00 | UVIS_FUV to Rocks | NEG_X to 129.055/62.502 | Collaborative Rider(s): CDA. Must point within 15 deg of 233/9
Apoapse Per = 23.9 d, inc ... |  | 2016-169T05:46:32 |  | 000T00:00:01 | 2016-169T05:46:33
SP_237EA_YGAP170_PRIME |  | 2016-170T05:45:00 |  | 000T01:30:00 | 2016-170T07:15:00 | XBAND to Earth | NEG_X to 141.0/-42.0
SP_237EA_C70METSEQ170_PRIME | C | 2016-170T07:15:00 |  | 000T09:00:00 | 2016-170T16:15:00 | XBAND to Earth | NEG_X to 141.0/-42.0 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_237SA_WAYPTTURN170_PRIME |  | 2016-170T16:15:00 |  | 000T00:30:00 | 2016-170T16:45:00 | ISS_NAC to Saturn | POS_Z to 191.4/52.8
NEW WAYPOINT |  | 2016-170T16:45:00 |  | 001T12:10:00 | 2016-172T04:55:00 | ISS_NAC to Saturn | POS_Z to 191.4/52.8
ISS_237TI_M90R3CLD170_PRIME | C, V | 2016-170T16:45:00 | E237_M90R3CLD170+000T00:00:00 | 000T01:30:00 | 2016-170T18:15:00 | ISS_NAC to Titan | POS_Z to 191.4/52.8 | No Preference to secondary pointing
ISS_237OT_SATELLORB001_PRIME | C, I, V | 2016-170T18:15:00 |  | 000T01:00:00 | 2016-170T19:15:00 | ISS_NAC to Satellites | POS_Z to 191.4/52.8 | Must point within 15 deg of Saturn Center
CIRS_237SA_COMPSIT001_PRIME | I, V | 2016-170T19:15:00 |  | 000T23:00:00 | 2016-171T18:15:00 | CIRS_FP1 to Saturn | POS_Z to 191.4/52.8
CIRS_237RA_COMPLLRES001_PRIME | C, U, V | 2016-171T18:15:00 |  | 000T10:00:00 | 2016-172T04:15:00 | CIRS_FP1 to Rings | POS_Z to 191.4/52.8 | No Preference to secondary pointing. Must point within 15 degrees of Saturn center
SP_237EA_DLTURN172_PRIME |  | 2016-172T04:15:00 |  | 000T00:40:00 | 2016-172T04:55:00 | XBAND to Earth | NEG_X to 322.0/40.0
NEW WAYPOINT |  | 2016-172T04:55:00 |  | 000T11:40:00 | 2016-172T16:35:00 | XBAND to Earth | NEG_X to 322.0/40.0
SP_237EA_YGAP172_PRIME |  | 2016-172T05:45:00 |  | 000T01:30:00 | 2016-172T07:15:00 | XBAND to Earth | NEG_X to 322.0/40.0
SP_237EA_C34BWGSEQ172_PRIME | C, E | 2016-172T07:15:00 |  | 000T09:00:00 | 2016-172T16:15:00 | XBAND to Earth | NEG_X to 322.0/40.0 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_237SA_WAYPTTURN172_PRIME |  | 2016-172T16:15:00 |  | 000T00:20:00 | 2016-172T16:35:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
NEW WAYPOINT |  | 2016-172T16:35:00 |  | 001T13:20:00 | 2016-174T05:55:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
ISS_237TI_M60R3CLD172_PRIME | C, V | 2016-172T16:35:00 | E237_M60R3CLD172+000T00:00:00 | 000T01:30:00 | 2016-172T18:05:00 | ISS_NAC to Titan | NEG_X to 191.4/52.8 | No Preference to secondary pointing
ISS_237OT_SATELLORB002_PRIME | I, V | 2016-172T18:05:00 |  | 000T01:00:00 | 2016-172T19:05:00 | ISS_NAC to Satellites | NEG_X to 191.4/52.8 | Must point within 15 deg of Saturn Center
CIRS_237RC_COMPLLRES001_PRIME | C, U, V | 2016-172T21:25:00 |  | 000T10:00:00 | 2016-173T07:25:00 | CIRS_FP1 to Rings | NEG_X to 191.4/52.8 | No Preference to secondary pointing. Must point within 15 degrees of Saturn center
VIMS_237RI_2CENCAL001_PRIME | C | 2016-173T07:25:00 |  | 000T02:00:00 | 2016-173T09:25:00 | VIMS_IR to 207.361/-34.451 | NEG_X to 191.4/52.8 | Must point within 15 degrees of Saturn center
VIMS_237RI_2CENOCC001_PRIME | C, I | 2016-173T09:25:00 |  | 000T20:05:00 | 2016-174T05:30:00 | VIMS_IR to 207.361/-34.451 | NEG_X to 191.4/52.8 | Must point within 15 degrees of Saturn center
SP_237EA_DLTURN174_PRIME |  | 2016-174T05:30:00 |  | 000T00:25:00 | 2016-174T05:55:00 | XBAND to Earth | NEG_X to 322.0/40.0
NEW WAYPOINT |  | 2016-174T05:55:00 |  | 000T10:35:00 | 2016-174T16:30:00 | XBAND to Earth | NEG_X to 322.0/40.0
SP_237EA_YGAP174_PRIME |  | 2016-174T05:55:00 |  | 000T01:30:00 | 2016-174T07:25:00 | XBAND to Earth | NEG_X to 322.0/40.0
SP_237EA_C70METSEQ174_PRIME | C, R | 2016-174T07:25:00 |  | 000T08:35:00 | 2016-174T16:00:00 | XBAND to Earth | NEG_X to 322.0/40.0 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_237SA_WAYPTTURN174_PRIME |  | 2016-174T16:00:00 |  | 000T00:30:00 | 2016-174T16:30:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
NEW WAYPOINT |  | 2016-174T16:30:00 |  | 001T13:00:00 | 2016-176T05:30:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
ISS_237TI_M30R3CLD174_PRIME | C, V | 2016-174T16:30:00 | E237_M30R3CLD174+000T00:00:00 | 000T01:30:00 | 2016-174T18:00:00 | ISS_NAC to Titan | NEG_X to 191.4/52.8 | No Preference to secondary pointing
VIMS_237ST_ALPSCOCAL001_PRIME |  | 2016-174T18:00:00 |  | 000T04:00:00 | 2016-174T22:00:00 | VIMS_IR to 247.352/-26.432 | POS_X to 359.0/-40.0 | Must point within 15 degrees of Saturn center
ISS_237OT_SATELLORB003_PRIME | C, I, V | 2016-174T22:00:00 |  | 000T01:00:00 | 2016-174T23:00:00 | ISS_NAC to Satellites | NEG_X to 191.4/52.8 | Must point within 15 deg of Saturn Center
ISS_237RI_ARCORBIT001_PRIME | C, I, V | 2016-174T23:00:00 |  | 000T22:55:00 | 2016-175T21:55:00 | ISS_NAC to Rings | NEG_X to 181.4/42.8 | Must point within 15 deg of Saturn Center
VIMS_237RI_APOMOSAIC001_PRIME | C, I, U | 2016-175T21:55:00 |  | 000T07:00:00 | 2016-176T04:55:00 | VIMS_IR to Rings | NEG_X to 191.4/52.8 | Must point within 15 degrees of Saturn center
SP_237EA_DLTURN175_PRIME |  | 2016-176T04:55:00 |  | 000T00:35:00 | 2016-176T05:30:00 | XBAND to Earth | NEG_X to 322.0/40.0
NEW WAYPOINT |  | 2016-176T05:30:00 |  | 000T11:00:00 | 2016-176T16:30:00 | XBAND to Earth | NEG_X to 322.0/40.0
ENGR_237SC_RWABIAS176_PRIME |  | 2016-176T05:30:00 |  | 000T01:30:00 | 2016-176T07:00:00 | XBAND to Earth | NEG_X to 322.0/40.0
SP_237EA_C34BWGSEQ176_PRIME | C, R | 2016-176T07:00:00 |  | 000T09:00:00 | 2016-176T16:00:00 | XBAND to Earth | NEG_X to 322.0/40.0 | No Roll due to AACS 2 of 3 Rule. Secondary chosen for CDA.
SP_237SA_WAYPTTURN176_PRIME |  | 2016-176T16:00:00 |  | 000T00:30:00 | 2016-176T16:30:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
NEW WAYPOINT |  | 2016-176T16:30:00 |  | 001T14:14:00 | 2016-178T06:44:00 | ISS_NAC to Saturn | NEG_X to 191.4/52.8
ISS_237TI_M30R3CLD176_PRIME | C, V | 2016-176T16:30:00 | E237_M30R3CLD176+000T00:00:00 | 000T01:30:00 | 2016-176T18:00:00 | ISS_NAC to Titan | NEG_X to Sun
MAG_237SU_CALROLL001_PRIME | U | 2016-176T18:00:00 |  | 000T08:00:00 | 2016-177T02:00:00 | NEG_X to Earth (0.0,0.0,-30.0 deg. offset) | Rolling
UVIS_237SA_AURSLEW002_PRIME | C, V | 2016-177T02:00:00 |  | 000T09:49:00 | 2016-177T11:49:00 | UVIS_FUV to Saturn | NEG_X to 191.4/52.8 | Must point within 15 deg of Saturn Center
VIMS_237RI_ALPSCOOCC001_PIE | C, I, U | 2016-177T11:49:00 |  | 000T10:16:00 | 2016-177T22:05:00 | VIMS_IR to 247.352/-26.432 | NEG_X to 177.625/35.058 | Must point within 15 degrees of Saturn center
NAV_237SK_OPNAV771_PRIME |  | 2016-177T22:05:00 |  | 000T01:30:00 | 2016-177T23:35:00 | ISS_NAC to Satellites | NEG_Z to 263.337/32.066 | Starts at waypoint, ends at same waypoint
VIMS_237RI_0PHASEC001_PRIME | C, I, U | 2016-177T23:35:00 |  | 000T05:25:00 | 2016-178T05:00:00 | POS_Y to Sun | NEG_X to 191.4/52.8 | Must point within 15 degrees of Saturn center
SP_237EA_DLTURN178_PRIME |  | 2016-178T06:10:00 |  | 000T00:34:00 | 2016-178T06:44:00 | XBAND to Earth | NEG_X to 352.0/-30.0
NEW WAYPOINT |  | 2016-178T06:44:00 |  | 000T09:00:00 | 2016-178T15:44:00 | XBAND to Earth | NEG_X to 352.0/-30.0
SP_237EA_C70METSEQ178_PRIME | C, E | 2016-178T06:44:00 |  | 000T09:00:00 | 2016-178T15:44:00 | XBAND to Earth | NEG_X to 352.0/-30.0 | CDA.NEG_X to 352/-30.EOS.